EIC PATHFINDER OPEN 2026

APPLICATION — FORM B

CDATA-LONGEVITY

Centriolar Damage Accumulation as a Universal Clock of Biological Aging:
From Computational Model to Validated Biomarker

SECTION 1 — EXCELLENCE

Max 12 pages. Criteria: Soundness of concept; Credibility of proposed approach; Transformative potential; Novelty beyond state-of-the-art.

1.1  Concept and Vision

Aging is the single largest risk factor for all chronic non-communicable diseases — cardiovascular disease, neurodegeneration, cancer, and metabolic syndrome — yet no mechanistic, quantitative, and experimentally falsifiable theory of its causation has reached clinical translation. The Centriolar Damage Accumulation Theory of Aging (CDATA) fills this gap.

CDATA proposes that the primary, irreversible driver of organismal aging is the progressive accumulation of post-translational modifications and structural damage to centriolar distal appendages — specifically to CEP164, CEP89, Ninein, and CEP170 — in adult stem cells. Damaged centrioles lose the ability to nucleate functional primary cilia; this disrupts niche signalling (Shh, Wnt, Notch), shifts stem-cell divisions from asymmetric (self-renewal) to symmetric (exhaustion or clonal expansion), and ultimately depletes the regenerative capacity of every tissue in a tissue-specific, ordered sequence.

This project — CDATA-LONGEVITY — will: (1) validate CDATA quantitative predictions against human biological samples across the adult lifespan; (2) establish a panel of centriolar integrity biomarkers measurable in peripheral blood; and (3) develop an open-source validated computational simulator as a precision longevity tool for both basic research and clinical risk stratification.

1.2  Novelty and Transformative Potential

CDATA differs categorically from existing aging theories:

| Feature | CDATA | Hallmarks of Aging (López-Otín) | Telomere Theory | Inflammaging |
| --- | --- | --- | --- | --- |
| Mechanistic causal driver | ✓ Single mechanism | ✗ 12 parallel hallmarks | Partial | ✗ Downstream effect |
| Quantitative predictions | ✓ Tissue ages, r>0.65 | ✗ Qualitative only | ✗ No lifespan prediction | ✗ |
| Unifies normal/longevity/progeria | ✓ Under 1 parameter set | ✗ | ✗ | ✗ |
| Concrete intervention target | ✓ CEP164/CEP89 repair | Partial | Telomerase | Anti-inflammatories |
| Computational falsifiable model | ✓ cell_dt, 198 tests | ✗ | ✗ | ✗ |

CDATA is the only aging theory that: (a) predicts the chronological order of tissue exhaustion (skin 50–55 y → intestinal crypts 55–60 y → haematopoietic 60–65 y → muscle 70–75 y → neural last); (b) unifies lifespan data for normal aging (76–78 y), longevity (95+ y), and Hutchinson-Gilford Progeria Syndrome (~20 y) under one parameter set; and (c) offers a concrete intervention target (centriolar appendage repair).

1.3  Scientific Foundation and Prior Work

CDATA rests on 20 years of peer-reviewed publications by the PI:

Tkemaladze J. & Chichinadze K. (2005). Centriolar mechanisms of differentiation and replicative aging of higher animal cells. Biochemistry (Moscow), 70(11).

Tkemaladze J. (2023). Reduction, proliferation, and differentiation defects of stem cells over time: a consequence of selective accumulation of old centrioles in the stem cells? Molecular Biology Reports, 50(3):2751–2761. DOI: 10.1007/s11033-022-08229-5.

Tkemaladze J. (2026). Old Centrioles Make Old Bodies. Annals of Rejuvenation Science, 1(1). DOI: 10.65649/yx9sn772.

[Accepted 2026] Tkemaladze J. (2026). CDATA computational simulation: validation against human biological aging trajectories. npj Aging (Nature Portfolio) — manuscript accepted March 2026. DOI: pending assignment.

The computational simulator (cell_dt, Rust, open source: github.com/djabbat/cell_dt) implements 6 molecular damage tracks (A: cilia loss; B: spindle failure; C: telomere shortening; D: epigenetic clock; E: mitochondrial dysfunction; F: division rate modulation), 11 tissue types, and passes 198 unit tests. Calibration demonstrates lifespan predictions within 2–3% of observed population medians across three aging phenotypes.

1.4  Methodology

Work Package 1 — Human Cohort Validation (months 1–24)

Design: Prospective cross-sectional study. n=288 enrolled (accounting for 20% dropout); minimum evaluable set n=240, age-stratified: 20–35 (n=60), 36–50 (n=60), 51–65 (n=60), 66–80 (n=60). Recruitment: Georgian Technical University (GTU), Tbilisi (Faculty of Biomedical Engineering) + Kutaisi International University Hospital.

Primary endpoint: Centriolar appendage integrity index (CAII) — super-resolution immunofluorescence (Ultrastructure Expansion Microscopy, U-ExM; ~20 nm lateral resolution) for CEP164, CEP89, Ninein, CEP170 in skin fibroblast biopsies; quantified as mean appendage length (nm) per centriole pair. U-ExM protocol: Gambarotto et al. (2019) Nat Methods 16:71–76. Confocal acquisition on Leica SP8 STED available at GTU Biomedical Engineering imaging core (77 Kostava St, Tbilisi).

Secondary endpoints: Primary cilia length & frequency; myeloid:lymphoid ratio (proxy for HSC asymmetric division failure); frailty index (SPPB battery); inflammatory panel (IL-6, TNF-α, CRP, GDF-15)

CDATA prediction to validate: CAII decreases monotonically with age at rate 0.0020–0.0027 /year per appendage protein (derived from calibrated cell_dt simulator track A parameters; see github.com/djabbat/cell_dt, configs/normal_aging.toml); correlation with frailty index r > 0.65 (predicted by myeloid_shift_module output at CAII < 0.7).

Work Package 2 — Peripheral Blood Biomarker (months 6–30)

Goal: Develop a minimally-invasive proxy for CAII using peripheral blood. Rationale: skin biopsy is impractical for population screening.

Approach: Isolate CD34+/CD133+/KDR+ early EPCs and CD14+ monocyte-derived macrophages from 20 ml EDTA blood by magnetic bead separation (Miltenyi MACS; CD34 MicroBeads + CD14 MicroBeads). Feasibility basis: EPC frequency in adults = 1–10 cells/ml; from 20 ml → 20–200 EPCs, sufficient for protein quantification by Proximity Ligation Assay (PLA detects single-molecule events). Protocol adapted from Vasa et al. (2001) Circ Res 89:e1–e7.

Measure CEP164 / Ninein protein levels by ELISA and proximity ligation assay

Train ML model (elastic net regression): CAII_skin ~ blood_proxy (train:test 70:30)

Deliverable: validated blood-based CAII proxy, sensitivity ≥ 0.80, specificity ≥ 0.75

Work Package 3 — Simulator Enhancement & Open Platform (months 1–36)

Extend cell_dt simulator to incorporate cohort validation data:

Bayesian parameter fitting: update track A–F rate constants from WP1 measurements

Add pharmacological intervention module: senolytics, NAD+ boosters, telomerase, caloric restriction — predict healthspan extension per intervention

Web API: /api/cdata/predict — input age + CAII → output frailty trajectory + intervention ranking

Deliverable: open-source CDATA v2.0 platform; Docker image; tutorial published on GitHub + Zenodo

Work Package 4 — Dissemination & Ethics (months 1–36)

Ethics approval: GTU Ethics Committee + Kutaisi University Hospital IRB (Month 1–3). Letters of Intent from GTU (Faculty of Biomedical Engineering) and KIU Hospital — Annex 1. Consortium Agreement (Phasis Academy ↔ GTU): drafted via EEN Georgia / GITA legal template, signed Month 1–2 (Milestone M0).

Data management plan: GDPR-compliant; data on EU-hosted repository (EUDAT B2SHARE)

Publications: ≥4 peer-reviewed (Nature Aging, Cell Reports, Aging Cell)

Open access: all papers gold OA; simulator MIT license; dataset CC-BY 4.0

Patent: blood-based CAII proxy as aging biomarker (month 18–24)

SECTION 2 — IMPACT

Criteria: Scientific impact; Societal & economic impact; Sustainability beyond grant period.

2.1  Scientific Impact

CDATA-LONGEVITY will deliver the first mechanistic, tissue-resolved, quantitatively falsifiable human validation study of a novel aging theory. Key scientific contributions:

First experimental confirmation (or falsification) of the CDATA theory in human tissue — a decisive scientific milestone regardless of outcome

First blood-based centriolar integrity proxy — enables population-level aging studies without biopsy

First computational simulator integrating all 6 CDATA tracks with prospective human data

Open platform enabling any research group worldwide to run patient-specific aging simulations

2.2  Societal and Economic Impact

Aging-related diseases cost the EU >€700 billion annually (EuroHealthNet, 2024). CDATA-LONGEVITY addresses this through:

Clinical stratification: identify patients at risk of accelerated aging 10–15 years before symptom onset

Drug development: CAII as primary endpoint in longevity drug trials — reduces trial duration and cost

Personalised prevention: lifestyle and pharmacological interventions ranked by predicted CAII impact

Economic: 1-year delay in age-related disability onset = €3,200/person/year saved (WHO HALE data)

2.3  Pathway to Innovation and TRL Progression

TRL 3 (proof of concept in silico) → TRL 5 (validated in relevant environment) within 36 months:

Month 12: CAII biomarker protocol validated in 60 subjects (TRL 4)

Month 24: Blood proxy assay validated (TRL 5); patent filed

Month 30: Open CDATA platform released; API integrated with AIM clinical AI

Month 36: 4 publications; regulatory pre-submission meeting (IVD pathway, EU MDR)

2.4  Sustainability

Post-grant sustainability through three streams:

Commercial: blood-based CAII kit licensed to IVD manufacturer; target revenue stream year 5 post-grant

Academic: CDATA platform as standard tool in aging research community (target: 500+ citations by year 5)

Clinical: integration of CAII into national preventive medicine programs. Georgia MoH discussions initiated (letter of intent from National Centre for Disease Control & Public Health of Georgia, [TO ATTACH]). EU partner: negotiation with Estonian Biobank (University of Tartu) for population-level CAII reference dataset post-grant.

SECTION 3 — IMPLEMENTATION

3.1  Consortium

Consortium Structure:

Beneficiary 1 — Lead: Phasis Academy (ფაზისის აკადემია), Poti, Georgia
Role: Project coordination, theory development, simulator (WP3), dissemination (WP4)
PIC number: [TO BE REGISTERED — contact a.goletiani@mes.gov.ge]
Georgia is an Associated Country to Horizon Europe (Association Agreement effective 2023); 100% reimbursement rate applies.

Beneficiary 2: Georgian Technical University (GTU) — ტექნიკური უნივერსიტეტი, Tbilisi, Georgia
Former name: Tbilisi State Polytechnic Institute (founded 1922)
PIC number: 983636358 (registered in EU Funding & Tenders Portal)
Faculty: Biomedical Engineering (ABET-accredited) + Faculty of Medicine
Horizon Europe track record: active participant (FORGE-AI, grant 101216703)
Role: Human cohort recruitment (WP1), super-resolution imaging core, blood biomarker laboratory (WP2), local IRB oversight
Scientific contact: Faculty of Biomedical Engineering, GTU (Dean's office: +995 32 2 36 02 85; bmegtu.wordpress.com). Administrative/international contact: International Relations Dept., adavitashvili@gtu.ge. Rector: Prof. David Gurgenidze, rectoroffice@gtu.ge
Address: 77 Kostava Street, 0171 Tbilisi, Georgia

Associated Partner (no EU funding): Kutaisi International University Hospital — clinical recruitment support, patient access

IP and Data: All IP generated belongs to the consortium (Phasis Academy — background IP on CDATA theory and cell_dt; GTU — foreground IP on CAII biomarker protocol and blood proxy assay). cell_dt simulator remains MIT-licensed open-source.

3.2  Work Plan and Milestones

The project is structured into 4 Work Packages over 36 months. WP1 and WP3 run in parallel from Month 1; WP2 begins at Month 6 once WP1 biopsy protocols are validated; WP4 spans the full project.

WP Leaders:
• WP1 (Cohort Validation): GTU, Faculty of Biomedical Engineering
• WP2 (Blood Biomarker): GTU, Faculty of Biomedical Engineering
• WP3 (Simulator Enhancement): Phasis Academy (Dr. Tkemaladze)
• WP4 (Dissemination & Ethics): Phasis Academy (Dr. Tkemaladze)

Person-months allocation:
• PI (Dr. Tkemaladze): WP1=6 PM, WP2=4 PM, WP3=18 PM, WP4=8 PM — Total: 36 PM
• Postdoc 1 (clinical, GTU): WP1=20 PM, WP2=14 PM, WP4=2 PM — Total: 36 PM
• Postdoc 2 (computational, Phasis): WP3=30 PM, WP4=4 PM — Total: 34 PM
• Clinical Coordinator (GTU): WP1=18 PM, WP2=6 PM, WP4=4 PM — Total: 28 PM

| Work Package | M1–6 | M7–12 | M13–18 | M19–24 | M25–30 | M31–36 |
| --- | --- | --- | --- | --- | --- | --- |
| WP1: Cohort Validation | ████ | ████ | ████ | ████ |  |  |
| WP2: Blood Biomarker |  | ████ | ████ | ████ | ████ |  |
| WP3: Simulator v2.0 | ████ | ████ | ████ | ████ | ████ | ████ |
| WP4: Dissemination & Ethics | ████ | ████ | ████ | ████ | ████ | ████ |

| Milestone | WP | Month | Deliverable | Verification |
| --- | --- | --- | --- | --- |
| M1: IRB approval | WP4 | 3 | Ethics approval documents | KIU IRB letter |
| M2: Biopsy protocol validated | WP1 | 6 | SOPs + 10 pilot biopsies | U-ExM images, κ>0.80 |
| M3: CAII measured in 60 subjects | WP1 | 12 | Dataset + statistical report | TRL 4 confirmed |
| M4: EPC isolation protocol validated | WP2 | 12 | PLA protocol SOP | Reproducibility in 10 donors |
| M5: CAII full cohort n=240 | WP1 | 24 | Full dataset + CDATA validation | p<0.05, r>0.65 |
| M6: Blood proxy assay validated | WP2 | 30 | ML model + sensitivity/specificity | Sens≥0.80, Spec≥0.75 |
| M7: Patent filed | WP4 | 24 | Patent application (blood CAII proxy) | Filing confirmation |
| M8: CDATA v2.0 released | WP3 | 30 | GitHub release + Docker image + API | 50+ downloads in 3 months |
| M9: 4 publications + TRL5 | WP4 | 36 | Accepted papers + regulatory meeting | DOIs + meeting minutes |

3.3  Budget Overview

Total budget: €2,500,000 (100% EIC Pathfinder Open funding rate). All costs are direct costs; indirect costs calculated at 25% flat rate per Horizon Europe rules.

| Work Package | Personnel | Equipment | Consumables | Other | WP Total |
| --- | --- | --- | --- | --- | --- |
| WP1: Cohort Validation | €380,000 | €180,000 | €180,000 | €60,000 | €800,000 |
| WP2: Blood Biomarker | €220,000 | €60,000 | €120,000 | €50,000 | €450,000 |
| WP3: Simulator Enhancement | €300,000 | €20,000 | €10,000 | €70,000 | €400,000 |
| WP4: Dissemination & Ethics | €180,000 | €0 | €20,000 | €150,000 | €350,000 |
| Indirect costs (25% flat rate) |  |  |  |  | €500,000 |
| TOTAL | €1,080,000 | €260,000 | €330,000 | €330,000 | €2,500,000 |

Key cost drivers: WP1 personnel (postdoc ×24 months + clinical coordinator), U-ExM microscopy upgrade (Leica SP8 STED, €120,000 — upgrade of GTU Zeiss LSM 700 core), biopsy consumables (n=288 enrolled × ~€625/subject). WP2: Miltenyi MACS reagents (n=240 × €500/subject). WP4: gold OA fees (4 × €4,500 = €18,000) + patent prosecution (€25,000) + Consortium Agreement legal support (€5,000 via EEN Georgia / GITA).

Equipment justification (Art.6.2.D HEU GA): Leica SP8 STED upgrade (€120,000) — GTU currently operates Zeiss LSM 700 (lateral resolution ~200 nm), insufficient for U-ExM nm-scale appendage measurement; upgrade provides ~20 nm lateral resolution required for CAII quantification. Equipment dedicated exclusively to CDATA-LONGEVITY protocol; post-project use governed by GTU open-access policy. Miltenyi MACS separator (€25,000) — no equivalent at GTU or KIU; required for WP2 EPC/monocyte isolation.

3.4  Principal Investigator — Dr. Jaba Tkemaladze, MD

MD, Tbilisi State Medical University; researcher at Georgian Technical University (GTU), Tbilisi; affiliated with Kutaisi International University

20+ years research in centriole biology and stem cell aging

Publications: Biochemistry (Moscow) 2005; Molecular Biology Reports 2023; Annals of Rejuvenation Science 2026; npj Aging 2026 (accepted)

Developed CDATA theory independently; implemented cell_dt simulator (Rust, 14 crates, 198 unit tests)

Active funding applications: EIC Pathfinder, MSCA, Rustaveli Foundation (Georgia)

Super-resolution microscopy expertise: hands-on experience with U-ExM (Ultrastructure Expansion Microscopy) and confocal protocols. PI trained in expansion microscopy at Tbilisi State Medical University core facility; GTU imaging core upgrade (Leica SP8 STED, budgeted in WP1 equipment, €120,000) will provide required ~20 nm lateral resolution for CAII quantification from Month 3.

3.5  Risk Mitigation

Per EIC Pathfinder review guidelines, the following risks are identified and mitigated:

Risk 1 — WP2 blood biomarker failure (HIGH impact / MEDIUM probability)
Description: EPC isolation from peripheral blood may yield insufficient cell numbers or low CEP164 signal for PLA quantification in the 66–80 age group.
Mitigation: (a) Pilot isolation in 20 donors before full WP2 launch (Month 6–8); if EPC yield <5 cells/ml in >30% of donors, switch primary cell type to CD14+ monocyte-derived macrophages (higher abundance: ~10% of PBMCs; also express CEP164). (b) Supplement ELISA/PLA with proximity extension assay (PEA, Olink platform) as orthogonal quantification. (c) If blood proxy fails to reach Sens≥0.80, project Impact is reduced but WP1 (skin biopsy CAII) and WP3 (simulator) remain fully valid and sufficient for primary CDATA validation.

Risk 2 — CAII correlation below prediction (r < 0.65) (HIGH impact / LOW probability)
Description: cell_dt predicts r > 0.65 between CAII and SPPB frailty index. If observed r < 0.65, this would not falsify CDATA but would indicate model recalibration is needed.
Mitigation: (a) Pre-specified adaptive analysis plan: if r < 0.65 at n=120 (interim analysis, Month 18), Bayesian model will be updated and CAII measurement protocol reviewed with a blinded statistical advisory board. (b) Secondary endpoints (cilia frequency, IL-6, myeloid:lymphoid ratio) provide additional falsification opportunities independent of CAII absolute values.

Risk 3 — Participant dropout in WP1 (MEDIUM impact / MEDIUM probability)
Description: 3 mm skin punch biopsy may deter volunteers, especially in the 66–80 age group.
Mitigation: (a) Enrolment target inflated to n=288 (20% dropout buffer); minimum evaluable set n=200. (b) Biopsy performed under trained dermatologist supervision; compensation provided per IRB-approved protocol. (c) Recruitment strategy: medical school volunteer pool (GTU + KIU) + Georgian Veterans Association + community health fairs.

Risk 4 — Consortium capacity / "bus factor" (MEDIUM impact / LOW probability)
Description: Dr. Tkemaladze as sole theory expert creates key-person dependency.
Mitigation: (a) All CDATA theory documentation, simulator, and protocols fully open-source and documented (GitHub: djabbat/cell_dt); project is continuable by any trained researcher. (b) GTU Biomedical Engineering faculty (Prof. Gela [Surname — pending GTU confirmation, ბატონი გელა, თუ თანახმაა]) serves as co-PI for clinical operations, providing institutional continuity. (c) Associated partner network (EEN Georgia / GITA) enables rapid identification of replacement expertise if needed.

SECTION 4 — ETHICS AND DATA MANAGEMENT

4.1  Ethics

All human studies subject to IRB approval (Georgian Technical University Ethics Committee (Tbilisi) + Kutaisi University Hospital IRB)

Written informed consent from all participants

No vulnerable populations in the formal sense; healthy adult volunteers only. Special provision for 66–80 age group: two-stage informed consent process (written + verbal confirmation at biopsy appointment); participants may withdraw at any time without consequences; cognitive screening (Mini-Cog, 3 minutes) administered at enrolment to confirm decision-making capacity, consistent with ICH E6(R2) GCP guidelines.

Biopsies: 3 mm punch biopsy under local anaesthesia — standard, minimal-risk procedure

GDPR compliance: pseudonymised data; no personal identifiers in datasets

Ethics self-assessment: no dual use, no animal experiments, no GMO

4.2  Data Management

All raw data stored on EUDAT B2SHARE (EU-hosted, FAIR principles)

Simulator code: MIT license, GitHub + Zenodo DOI at each release

Datasets: CC-BY 4.0 upon publication

Retention: 10 years post-project (per Horizon Europe requirements)

Data Management Plan submitted within 6 months of project start (standard)

4.3  Open Science

All publications: Gold Open Access (APC covered in budget)

Preprints on bioRxiv at submission time

Simulator: open-source, documented, reproducible (Docker image)

CDATA platform API: free academic use, paid commercial licence

CDATA-LONGEVITY | EIC Pathfinder Open 2026 | Dr. Jaba Tkemaladze | ფაზისის აკადემია | Deadline: 12 May 2026